This timeline integrates the implementation phases with the cohort launch strategy.

Phase 1: Foundation & Core Systems (Weeks 1-4)

- Goal: Establish basic infrastructure for both device and cloud.

- Activities:

  - Setup cloud infrastructure (Auth, Registry placeholders).

  - Basic Android app shell creation (UI framework, navigation).

  - Initial MCP server implementation on Android.

  - Define core data schemas (consent, query, user).

  - Setup CI/CD pipelines.

- Milestone: Core systems can communicate; basic user registration flow functional.

Phase 2: Device Logic & Local Enforcement (Weeks 5-8)

- Goal: Implement core on-device query processing and consent enforcement.

- Activities:

  - Develop Consent Manager logic.

  - Implement Query Evaluator.

  - Integrate initial Data Collectors (e.g., device info, basic sensors).

  - Build Data Formatter for MCP responses.

  - Implement Performance Manager basics.

  - Develop local Audit Logger.

  - Begin internal alpha testing on device farm.

- Milestone: Device can receive a query, check consent, collect basic data, format a response, and log the action locally. Battery/performance monitoring active.

Phase 3: Developer Integration & Payments (Weeks 9-12)

- Goal: Enable developer interaction and establish the earnings mechanism.

- Activities:

  - Build Developer Portal UI (Query Builder, basic Analytics, Sandbox).

  - Finalize Device Registry logic for query routing.

  - Implement Payment Processor logic (calculation based on logs).

  - Integrate real payment gateway (test environment).

  - Develop Consent Sync mechanism (cloud coordination).

  - Refine Authentication for developers.

  - Prepare developer documentation & basic SDK.

- Milestone: Developers can register, build/test queries via the portal, and receive test responses from alpha devices. Initial (test) payment calculations occur.

Phase 4: Cohort Onboarding & Testing (Weeks 13-16)

- Goal: Bring the pilot cohort online and gather real-world feedback.

- Activities:

  - Onboard 100 users & 10 developers (staggered).

  - Deploy Android app to users.

  - Provide developers access to the portal and SDK.

  - Enable live queries and real earnings tracking.

  - Intensive monitoring (telemetry, logs, performance).

  - Active feedback collection (surveys, check-ins).

  - Issue triage and rapid patch deployment.

- Milestone: System operating with the pilot cohort; data flowing, earnings accumulating; feedback loop established. First real payouts processed.

Phase 5: Validation & Refinement (Weeks 17-20)

- Goal: Analyze performance, validate metrics, refine UX, and prepare for post-MVP.

- Activities:

  - Analyze collected telemetry and feedback.

  - Benchmark system against success metrics (battery, latency, satisfaction).

  - Conduct cohort debrief interviews.

  - Final UX polish on app and portal based on feedback.

  - Validate payment accuracy and traceability.

  - Prepare MVP report and findings.

  - Plan next steps (scaling, feature expansion, open-sourcing).

- Milestone: MVP complete. Performance validated. Learnings documented. Ready for public summary and next phase planning.